## Standards Issues
Standard | Variant/Level | Requirement ID | Requirement Text | Implementation Status | Weaknesses | Responsible Office/Organization | Resources Estimate (Funded / Unfunded / Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete)
NIST CSF | NIST CSF | ID.AM-5 | Resource and Data Prioritization: ID.AM-5: Resources (e.g., hardware, devices, data, and software) are prioritized based on their classification, criticality, and business value | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.AC-5 | Network integrity: PR.AC-5: Network integrity is protected, incorporating network segregation where appropriate. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.AT-1 | Training: PR.AT-1: All users are informed and trained. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.DS-3 | Asset management: PR.DS-3: Assets are formally managed throughout removal, transfers, and disposition. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.DS-4 | Capacity: PR.DS-4: Adequate capacity to ensure availability is maintained | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.DS-5 | Data leak protection: PR.DS-5: Protections against data leaks are implemented | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.DS-7 | Development & testing environments: PR.DS-7: The development and testing environment(s) are separate from the production environment | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.IP-4 | Backups: PR.IP-4: Backups of information are conducted, maintained, and tested periodically | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.IP-6 | Data destruction: PR.IP-6: Data is destroyed according to policy. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.IP-7 | Continuous improvement: PR.IP-7: Protection processes are continuously improved. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | PR.IP-11 | Human Resource practices: PR.IP-11: Cybersecurity is included in human resources practices (e.g., deprovisioning, personnel screening) | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | DE.CM-4 | Malicious code detection: DE.CM-4: Malicious code is detected | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | RS.CO-2 | Event reporting: RS.CO-2: Events are reported consistent with established criteria. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | RS.CO-5 | Voluntary information sharing: RS.CO-5: Voluntary information sharing occurs with external stakeholders to achieve broader cybersecurity situational awareness | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | RS.AN-4 | Categorize incidents: RS.AN-4: Incidents are categorized consistent with response plans. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing
NIST CSF | NIST CSF | RS.IM-1 | Response lessons learned: RS.IM-1: Response plans incorporate lessons learned. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement policies, procedures, and required controls |  | Security and compliance assessment | Ongoing

## Control Issues
Control ID | Control Text | Implementation Status | Weaknesses | Responsible Office/Organization | Resources Estimate (Funded / Unfunded / Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete)
CC7.5 | Network Segregation: Protect network integrity, incorporating network segregation where appropriate. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC7.6 | HR Cybersecurity Alignment: Ensure that cybersecurity is included in human resources practices (e.g., deprovisioning, personnel screening). | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 |  |  | Security and compliance assessment | Ongoing
CC8.2 | Manage Assets: Ensure assets are formally managed throughout removal, transfers, and disposition. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC8.3 | Ensure Adequate Capacity: Ensure there is adequate capacity to ensure availability is maintained. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC8.4 | Protect Against Data Leaks: Protections against data leaks are implemented. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC8.6 | Separate Development & Testing Environments: Separate development and testing environment(s) from the production environment. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC8.10 | Data Destruction: Ensure data is destroyed according to policy, including deleting data no longer required for business purposes, and beyond any regulated retention period. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC8.13 | Improve Processes: Continuously improve data protection processes. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC14.1 | Business Continuity & Disaster Recovery Plans: Write effective Business Continuity and Disaster Recovery plans that meet all regulatory requirements and are in place and managed. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC14.2 | Resource Criticality: Establish and communicate the criticality of all resources. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC14.13 | Backups: Ensure all business-critical and regulated data is backed up regularly to meet the organization's recovery priorities. Include local devices, hosted environments, and software-as-a-service platforms. Backups must be complete and comprehensive enough to restore critical functions. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC14.15 | Restoration Testing: Ensure that backups are fully tested on a regular schedule to ensure that recoveries can take place as planned. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC14.18 | Recovery Capability Testing: Ensure that restoration testing proves that the RTO and RPO's can be met. If not, adjust the RTO and RPO to what has been proven to be possible, or change the proceses to meet the desired RTO and RPO. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC16.1 | Workforce Training: Implement workforce training that covers all required policies and procedures. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC17.1 | Vulnerability Scans: Scan for vulnerabilities and encryption status in organizational systems and applications periodically and when new vulnerabilities affecting those systems and applications are identified. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC18.12 | Malicious Code Detection: Ensure that malicious code is detected. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC19.6 | Categorize Incidents: Ensure that incidents are categorized consistent with response plans. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC19.15 | Incident Reporting Determination: Determine that the incident meets the requiremends for reporting. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC19.16 | Incident Documentation & Reporting: Ensure that events are documented and reported consistent with established criteria, including all legal and regulatory requirements. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC19.20 | Stakeholder Information Sharing: Ensure that voluntary information sharing occurs with external stakeholders to achieve broader cybersecurity situational awareness, consistent with response plans, legal advice, law enforcement requirements, and direction from the insurance company. | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing
CC19.21 | Response Plan Lessons Learned: | Not Implemented | Security and compliance assessment | New York, NY USA | Unfunded | Dec-31-2023 | Implement control |  | Security and compliance assessment | Ongoing

## Technical Issues
Implementation Status | Weaknesses | Affects | Responsible Office/Organization | Resources Estimate (Funded/Unfunded/Reallocation) | Scheduled Completion Date | Milestones | Changes to Milestones | How was the weakness identified | Status (Ongoing or Complete)
Not Implemented | Security and compliance assessment | DESKPC-35EGQCC / fe80::a03d:7987:35a4:7be%3,176.16.1.179 / Windows 10 Enterprise Version 2004 DESKPC-09UPSPO / 176.16.1.169 / Windows 10 Pro Version 1909 DESKPC-I595F9F / 176.16.1.102 / Windows 10 Enterprise Version 2004 DESKPC-N883DVI / 176.16.1.124 / Windows 10 Enterprise Version 2004 DESKPC-FOP1ENA / 176.16.1.136 / Windows 10 Enterprise Version 2004 DESKPC-5GTVFB3 / 176.16.1.131 / Windows 10 Enterprise Version 2004 DESKPC-3IC4R57 / fe80::9e8:6dd8:fe24:8c05%6,176.16.1.142 / Windows 10 Enterprise Version 2004 DESKPC-B9ETSS8 / 176.16.1.145 / Windows 10 Enterprise Version 2004 DESKPC-1QSHT11 / 176.16.1.140 / Windows 10 Enterprise Version 2004 DESKPC-Q9TQ4IM / 176.16.1.69 / Windows 10 Pro Version 2004 DESKPC-KLR129U / 176.16.1.51 / Windows 10 Pro Version 2004 DESKPC-ELBLDBS / 176.16.1.133 / Windows 10 Enterprise Version 2004 DESKPC-FEQIJCC / 176.16.1.146 / Windows 10 Enterprise Version 2004 DESKPC-4PF2ICP / 176.16.1.177 / Windows 10 Pro Version 1909 DESKPC-HQJ7BG2 / 176.16.1.139 / Windows 10 Enterprise Version 2004 | New York, NY USA | Unfunded | Dec-31-2023 | Upgrade or replace computers with operating systems that are no longer supported. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | Computer: DESKPC-F6CKERQ IP Address: 176.16.1.171 Security Center: Windows Defender Computer: DESKPC-BDJFFLG IP Address: 176.16.1.170 Security Center: Windows Defender Computer: DESKPC-LIFRCFU IP Address: 176.16.1.172 Security Center: Windows Defender Computer: DESKPC-35EGQCC IP Address: 176.16.1.179 Security Center: Windows Defender Computer: WRKSTN10-4 IP Address: 176.16.1.149 Security Center: Windows Defender | New York, NY USA | Unfunded | Dec-31-2023 | Ensure anti-spyware definitions are up to date on specified computers. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | Computer: DESKPC-HN95P9Q IP Address: 176.16.1.193 Security Center: Windows Defender Computer: DESKPC-F6CKERQ IP Address: 176.16.1.171 Security Center: Windows Defender Computer: DESKPC-BDJFFLG IP Address: 176.16.1.170 Security Center: Windows Defender Computer: DESKPC-LIFRCFU IP Address: 176.16.1.172 Security Center: Windows Defender Computer: DESKPC-QFC42PE IP Address: 176.16.1.182 Security Center: Windows Defender Computer: DESKPC-35EGQCC IP Address: 176.16.1.179 Security Center: Windows Defender | New York, NY USA | Unfunded | Dec-31-2023 | Ensure anti-virus definitions are up to date on specified computers. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | APPSVR01 / fe80::4183:7729:9818:eb0f%6,176.16.1.14 / Windows Server 2016 Standard DESKPC-35EGQCC / fe80::a03d:7987:35a4:7be%3,176.16.1.179 / Windows 10 Enterprise Version 2004 | New York, NY USA | Unfunded | Dec-31-2023 | Address patching on computers missing 1-3 security patches. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | DESKPC-4PF2ICP - C: : 0.05 GB free | New York, NY USA | Unfunded | Dec-31-2023 | Free or add additional disk space for the specified drives. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | abwfrcmbr / A Branaugh ajwfrcmbr / A Jensen aswfrcmbr / A Smith Administrator / Administrator dwfrcmbr / Dora Baxter dkwfrcmbr / D Kindle dwwfrcmbr / D White jswfrcmbr / J Shearing jwwfrcmbr / J Westerfield lwwfrcmbr / L Wilson mgwfrcmbr / M Green mpwfrcmbr / M Peters mwwfrcmbr / M Warly pkwfrcmbr / P Kettering pswfrcmbr / P Sulu skwfrcmbr / S Kulynee spwfrcmbr / S Podsekin thwfrcmbr / T Harris uwfrcmbr / unitbdr admin wpwfrcmbr / W Paulson ydwfrcmbr / Yami Dareloth ylwfrcmbr / Y Leland | New York, NY USA | Unfunded | Dec-31-2023 | Evaluate the need to have more than 30% of users in the Domain Administrator group and limit administrative access to the minimum necessary. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | MYCO.COM\aswfrcmbr / A Smith MYCO.COM\dwfrcmbr / Dora Baxter MYCO.COM\dkwfrcmbr / D Kindle MYCO.COM\jswfrcmbr / J Shearing MYCO.COM\jwwfrcmbr / J Westerfield MYCO.COM\lwwfrcmbr / L Wilson MYCO.COM\mgwfrcmbr / M Green MYCO.COM\mpwfrcmbr / M Peters MYCO.COM\pkwfrcmbr / P Kettering MYCO.COM\spwfrcmbr / S Podsekin MYCO.COM\thwfrcmbr / T Harris MYCO.COM\ydwfrcmbr / Yami Dareloth MYCO.COM\ylwfrcmbr / Y Leland MYCO.COM\ajwfrcmbr / A Jensen MYCO.COM\dwwfrcmbr / D White MYCO.COM\mtalman / M Talman MYCO.COM\mwwfrcmbr / M Warly MYCO.COM\pswfrcmbr / P Sulu MYCO.COM\uwfrcmbr / unitbdr admin MYCO.COM\wpwfrcmbr / W Paulson | New York, NY USA | Unfunded | Dec-31-2023 | Investigate all accounts with passwords set to never expire and configure them to expire regularly. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | DESKPC-RB3LBP3 / 176.16.1.108 / Windows 10 Enterprise 2015 LTSB APPSVR01 / fe80::4183:7729:9818:eb0f%6,176.16.1.14 / Windows Server 2016 Standard SQL01 / 176.16.1.17 / Windows Server 2012 R2 Standard EXCH01 / 176.16.1.15 / Windows Server 2012 R2 Standard FS01 / 176.16.1.16 / Windows Server 2016 Standard SQL02 / 176.16.1.21 / Windows Server 2016 Standard DCTRL01 / 176.16.1.12 / Windows Server 2016 Standard DCTRL02 / 176.16.1.13 / Windows Server 2016 Standard | New York, NY USA | Unfunded | Dec-31-2023 | Upgrade computers that have operating systems in Extended Support before end of life. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | WRKSTN7-2 / 176.16.1.115 / Windows 7 Professional WRKSTN8-3 / 176.16.1.136 / Windows 8.1 Pro WRKSTN8-2 / 176.16.1.131 / Windows 8.1 Pro BDR01 / 176.16.1.140 / Windows Server 2016 Standard WRKSTN10-2 / 176.16.1.143 / Windows 10 Enterprise WRKSTN8-1 / 176.16.1.128 / Windows 8.1 Pro WRKSTN7-1 / 176.16.1.126 / Windows 7 Professional WRKSTN10-3 / 176.16.1.141 / Windows 10 Enterprise WRKSTN8-4 / 176.16.1.137 / Windows 8.1 Pro WS2012IT / 176.16.1.135 / Windows Server 2012 Standard Evaluation RFHVNDA1 / 176.16.1.11 / Windows Server 2016 Standard | New York, NY USA | Unfunded | Dec-31-2023 | Investigate the list of inactive computers and determine if they should be removed from Active Directory, rejoined to the network, logged into by authorized users, or powered on. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | ajwfrcmbr / A Jensen arom / Axel Rom Administrator / Administrator backslash / back slash dwwfrcmbr / D White ebaldwin / Edward Baldwin fowardslash / fowared slash jknightling / Jorge Knightling jasus / Jeremy Asus jgilligan / Julia Gilligan jkalo / Jessica Kalo jchestnut / Janet Chestnut jconway / Joseph Conway jdelaney / Jonah Delaney mwwfrcmbr / M Warly mjohnson / Maxwell Johnson mtalman / M Talman pwalker / Paula Walker pswfrcmbr / P Sulu sjane / Sonny Jane tshelman / Terri Shelman uwfrcmbr / unitbdr admin wpwfrcmbr / W Paulson | New York, NY USA | Unfunded | Dec-31-2023 | Disable or remove user accounts for users that have not logged on to active directory in 30 days. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment |  | New York, NY USA | Unfunded | Dec-31-2023 | Enable password complexity to assure that network user account passwords are secure. |  | Security and compliance assessment | Ongoing
Not Implemented | Security and compliance assessment | APPSVR01 DESKPC-35EGQCC DESKPC-3IC4R57 DESKPC-534MS45 | New York, NY USA | Unfunded | Dec-31-2023 | Enable automatic screen lock on the specified computers. |  | Security and compliance assessment | Ongoing